## Sheet1
Gap ID | Area | Current State | Future State | Priority | Owner | Mitigation
GAP-001 | Order Entry | Manual validations in VA01 | Automated in Fiori app | High | Aryan Gupta | Pre-configure validation logic
GAP-002 | Pricing | 18+ cond. types/complex routine | 10 types; streamlined config | High | Aryan Gupta | Standardize before migration
GAP-003 | Customer Master | KNA1 only, duplicate risk | Unified BP master (CVI complete) | High | Aryan Gupta | Complete CVI, cleanse data
GAP-004 | Order Tracking | No real-time visibility | Fiori dashboards/notifications | Medium | Aryan Gupta | Implement order status APIs
GAP-005 | Testing | Manual, ad hoc scripts | Documented test scenarios | Medium | Aryan Gupta | Pre-migration test plan