## Sheet1
Risk ID | Description | Probability | Impact | Mitigation
R-001 | Data errors in CVI conversion | Medium | High | Cleanse/test before
R-002 | Pricing config regression | Low | Medium | Regression tests
R-003 | User resistance to Fiori interface | High | Medium | Training docs/video
R-004 | Output type migration issues | Medium | Low | Test all outputs